## Summary
Everlast Welders — Action Tracker
Sample for review, prepared Oct 16, 2026. Edit Status, Priority and Due on the Actions sheet; counts below update automatically.
Legend: yellow cells on the Actions sheet are the ones to edit (Status, Priority, Due).
Measure | Count
Open actions (not Done) | 30
Priority 1 open | 16
Priority 2 open | 10
Priority 3 open | 4
Follow-ups open | 6
Open questions | 5
Owner's items open | 11
Overdue (past due, not Done) | 0
Done | 0

## Actions
ID | Action | Type | Priority | Owner | Due | Days to due | Status | Area | Next step | Playbook
A02 | Confirm QuickBooks Online is the ledger and get accountant access | Follow-up | P1 | Owner | 2026-10-20 | 4 | Waiting | Setup | Owner sends accountant invite from QuickBooks settings | PB-COA
A03 | Accrual or cash basis? Calendar or fiscal year? | Open question | P1 | Owner | 2026-10-20 | 4 | Open | Setup | Confirm with CPA; plan assumes accrual, calendar year | PB-COA
A08 | Is inventory tracked in QuickBooks or a separate system? | Open question | P1 | Owner | 2026-10-20 | 4 | Open | Inventory | Decides how COGS and stock reports are built | PB-INV
A04 | Get access to website store, Amazon and payment processor reports | Follow-up | P1 | Owner | 2026-10-21 | 5 | Waiting | Sales channels | Read-only report access for each channel | PB-REC
A06 | Map current chart of accounts to product-line and channel structure | To-do | P1 | Bookkeeper | 2026-10-23 | 7 | Not started | Setup | Export current accounts; draft mapping for owner review | PB-COA
A05 | Reconcile Q3 2026 (Jul–Sep) bank, card and processor accounts | To-do | P1 | Bookkeeper | 2026-10-28 | 12 | Not started | Reconciliation | Starting point for clean quarterly reports | PB-REC
A01 | Deliver Forecasting & Inventory Operations report for the new-year order | To-do | P1 | Bookkeeper | 2026-10-30 | 14 | In progress | Forecasting | Pull 2025 and 2026 unit sales by SKU; draft reorder quantities | PB-INV
A16 | Seasonal Inventory sample: stock on hand vs last Nov–Dec sales by SKU | To-do | P1 | Bookkeeper | 2026-11-02 | 17 | Not started | Inventory | Flag SKUs at risk of selling out before Christmas | PB-INV
A14 | Deliver Q3 Financial & Cost Intelligence report | To-do | P1 | Bookkeeper | 2026-11-06 | 21 | Not started | Reporting | Depends on Q3 reconciliation | PB-CLOSE
A15 | Deliver Q3 Sales & Pricing report | To-do | P1 | Bookkeeper | 2026-11-06 | 21 | Not started | Reporting | Margin by product line and channel | PB-CLOSE
A18 | October month-end close | To-do | P1 | Bookkeeper | 2026-11-13 | 28 | Not started | Close | Target: business day 10 | PB-CLOSE
A21 | November month-end close | To-do | P1 | Bookkeeper | 2026-12-14 | 59 | Not started | Close | Target: business day 10 | PB-CLOSE
A22 | Full physical inventory count | To-do | P1 | Owner | 2026-12-31 | 76 | Not started | Inventory | Year-end valuation | PB-COUNT
A23 | December close and year-end packet for the CPA | To-do | P1 | Bookkeeper | 2027-01-15 | 91 | Not started | Year-end | Includes fixed asset review | PB-CLOSE
A24 | Deliver Q4 Financial & Sales reports | To-do | P1 | Bookkeeper | 2027-01-15 | 91 | Not started | Reporting | Oct–Dec 2026 | PB-CLOSE
A25 | 1099 contractor list and W-9 check | To-do | P1 | Bookkeeper | 2027-01-22 | 98 | Not started | Year-end | Contractors paid $600 or more | PB-AP
A07 | Are dealers sold on credit terms? Which terms? | Open question | P2 | Owner | 2026-10-22 | 6 | Open | Receivables | Sets the collections schedule | PB-AR
A09 | Supplier currency, and are deposits paid before shipment? | Open question | P2 | Owner | 2026-10-22 | 6 | Open | Inventory | Needed for landed cost and in-transit tracking | PB-LC
A17 | Send dealer past-due reminders (7, 30, 45 days) | Follow-up | P2 | Bookkeeper | 2026-10-23 | 7 | Not started | Receivables | Run AR aging; send reminders by tier | PB-AR
A28 | Owner approval of this week's payment run | Follow-up | P2 | Owner | 2026-10-23 | 7 | Waiting | Payables | Recurring every Friday | PB-AP
A11 | Set up clearing accounts for each processor and marketplace | To-do | P2 | Bookkeeper | 2026-10-27 | 11 | Not started | Reconciliation | One clearing account per payout source | PB-REC
A10 | Confirm sales tax nexus states with the CPA | Follow-up | P2 | CPA | 2026-10-30 | 14 | Waiting | Sales tax | List states with economic or physical nexus | PB-CLOSE
A12 | Build landed-cost template for import shipments | To-do | P2 | Bookkeeper | 2026-11-04 | 19 | Not started | Inventory | Spread freight, duties and brokerage by value | PB-LC
A13 | Set up warranty reserve account and monthly accrual rate | To-do | P2 | Bookkeeper | 2026-11-06 | 21 | Not started | COGS & warranty | Base the rate on the last 12 months of claims | PB-CLOSE
A20 | Quarterly cycle count of top 20% of SKUs | To-do | P2 | Owner | 2026-12-11 | 56 | Not started | Inventory | Before the holiday rush peaks | PB-COUNT
A26 | Full-year 2026 report | To-do | P2 | Bookkeeper | 2027-01-29 | 105 | Not started | Reporting | Then resume quarterly | PB-CLOSE
A30 | Who receives the monthly reporting packet? | Open question | P3 | Owner | 2026-10-30 | 14 | Open | Reporting | Names and delivery format | PB-CLOSE
A27 | Compare supplier statements to the ledger | Follow-up | P3 | Bookkeeper | 2026-11-10 | 25 | Not started | Payables | Monthly; resolve differences before close | PB-AP
A19 | Set QuickBooks user roles and lock closed periods | To-do | P3 | Owner | 2026-11-13 | 28 | Not started | Controls | Least access each role needs | PB-CLOSE
A29 | Social Media & Demand Generation sample | To-do | P3 | Bookkeeper | 2026-11-13 | 28 | Not started | Reporting | Ad spend vs sales by channel | PB-INV
Formulas:
Days to due = IF([Status]="Done","",[Due]-TODAY())

## Playbooks
Playbook | Title | Frequency | Step | Instruction | Owner | Done?
PB-CLOSE | Month-end close | Monthly | 1 | Reconcile every bank, credit card and loan account | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 2 | Clear each processor and marketplace clearing account | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 3 | Receive all inventory shipments and post landed costs | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 4 | Post inventory adjustments from counts and returns | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 5 | Accrue warranty reserve and unpaid bills | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 6 | Review AR and AP aging for errors and stale items | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 7 | Confirm sales tax liability matches filed returns | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 8 | Review P&L and balance sheet vs last month and last year | Owner
PB-CLOSE | Month-end close | Monthly | 9 | Lock the period in QuickBooks | Bookkeeper
PB-CLOSE | Month-end close | Monthly | 10 | Deliver the monthly reporting packet | Bookkeeper
PB-REC | Sales channel reconciliation | Weekly and monthly | 1 | Record gross sales by product line from each channel's report | Bookkeeper
PB-REC | Sales channel reconciliation | Weekly and monthly | 2 | Record fees, refunds, chargebacks and shipping as separate lines | Bookkeeper
PB-REC | Sales channel reconciliation | Weekly and monthly | 3 | Post the net payout from the clearing account to the bank deposit | Bookkeeper
PB-REC | Sales channel reconciliation | Weekly and monthly | 4 | Confirm each clearing account is zero or holds known in-transit payouts | Bookkeeper
PB-REC | Sales channel reconciliation | Weekly and monthly | 5 | Match returned units to restocked inventory or a write-off | Bookkeeper
PB-AR | Dealer collections | Weekly | 1 | Invoice the dealer the day the order ships | Bookkeeper
PB-AR | Dealer collections | Weekly | 2 | Day 7 past due: friendly reminder with invoice attached | Bookkeeper
PB-AR | Dealer collections | Weekly | 3 | Day 30 past due: firm reminder and phone call | Bookkeeper
PB-AR | Dealer collections | Weekly | 4 | Day 45 past due: owner call; consider holding new orders | Owner
PB-AR | Dealer collections | Weekly | 5 | Log every contact in the customer record | Bookkeeper
PB-AP | Bills and payment run | Weekly | 1 | Enter and code new vendor bills by Wednesday | Bookkeeper
PB-AP | Bills and payment run | Weekly | 2 | Match each bill to its PO and receiving count | Bookkeeper
PB-AP | Bills and payment run | Weekly | 3 | Send the proposed payment list to the owner Thursday | Bookkeeper
PB-AP | Bills and payment run | Weekly | 4 | Owner approves the run Friday | Owner
PB-AP | Bills and payment run | Weekly | 5 | Release payments and attach remittance to each bill | Bookkeeper
PB-LC | Landed cost for an import shipment | Per shipment | 1 | Hold the supplier bill in Inventory in transit | Bookkeeper
PB-LC | Landed cost for an import shipment | Per shipment | 2 | Collect freight, duties, brokerage and drayage bills | Bookkeeper
PB-LC | Landed cost for an import shipment | Per shipment | 3 | Spread those costs across units by value or weight | Bookkeeper
PB-LC | Landed cost for an import shipment | Per shipment | 4 | Receive units at full landed cost when counted in | Owner
PB-LC | Landed cost for an import shipment | Per shipment | 5 | Compare landed cost per unit to the last shipment | Bookkeeper
PB-INV | Seasonal inventory and reorder review | Before each season | 1 | Pull unit sales by SKU for the same months last year | Bookkeeper
PB-INV | Seasonal inventory and reorder review | Before each season | 2 | Compare to stock on hand plus open POs | Bookkeeper
PB-INV | Seasonal inventory and reorder review | Before each season | 3 | Flag SKUs with under 6 weeks of cover | Bookkeeper
PB-INV | Seasonal inventory and reorder review | Before each season | 4 | List slow movers to discount instead of reorder | Bookkeeper
PB-INV | Seasonal inventory and reorder review | Before each season | 5 | Owner signs off the reorder list | Owner
PB-COUNT | Inventory count | Quarterly and Dec 31 | 1 | Freeze receiving and shipping during the count | Owner
PB-COUNT | Inventory count | Quarterly and Dec 31 | 2 | Count by bin with two people per area | Owner
PB-COUNT | Inventory count | Quarterly and Dec 31 | 3 | Enter counts and review differences over 2% | Bookkeeper
PB-COUNT | Inventory count | Quarterly and Dec 31 | 4 | Post adjustments to Inventory adjustments and shrink | Bookkeeper
PB-COUNT | Inventory count | Quarterly and Dec 31 | 5 | Note causes and fixes for repeat differences | Owner
PB-COA | Chart of accounts setup | Once, then yearly | 1 | Export the current chart of accounts | Bookkeeper
PB-COA | Chart of accounts setup | Once, then yearly | 2 | Map revenue and COGS to product lines | Bookkeeper
PB-COA | Chart of accounts setup | Once, then yearly | 3 | Set up classes for each sales channel | Bookkeeper
PB-COA | Chart of accounts setup | Once, then yearly | 4 | Add warranty, clearing and in-transit accounts | Bookkeeper
PB-COA | Chart of accounts setup | Once, then yearly | 5 | Owner reviews and approves the new structure | Owner

## Close checklist
Business day | Step | Owner | Oct close | Nov close | Dec close
1 | Reconcile every bank, credit card and loan account | Bookkeeper
2 | Clear each processor and marketplace clearing account | Bookkeeper
3 | Receive all inventory shipments and post landed costs | Bookkeeper
4 | Post inventory adjustments from counts and returns | Bookkeeper
5 | Accrue warranty reserve and unpaid bills | Bookkeeper
6 | Review AR and AP aging for errors and stale items | Bookkeeper
7 | Confirm sales tax liability matches filed returns | Bookkeeper
8 | Review P&L and balance sheet vs last month and last year | Owner
9 | Lock the period in QuickBooks | Bookkeeper
10 | Deliver the monthly reporting packet | Bookkeeper
| Steps done (mark each with ✓) |  | 0 of 10 | 0 of 10 | 0 of 10
Due: Oct close Nov 13, 2026 · Nov close Dec 14, 2026 · Dec close and year-end packet Jan 15, 2027

## Operating rhythm
Frequency | Task
Daily | Categorize bank and card feeds
Daily | Record customer deposits
Daily | Flag large or unusual transactions
Weekly | Import sales summaries from each channel
Weekly | Enter and code vendor bills
Weekly | Send dealer invoices; chase past-due
Weekly | Match processor payouts to deposits
Monthly | Reconcile bank, card and processor accounts
Monthly | Post inventory and COGS adjustments
Monthly | Accrue warranty reserve
Monthly | Record payroll by department
Monthly | File sales tax returns as due
Monthly | Close books; deliver reporting packet
Quarterly | Cycle count top-selling SKUs
Quarterly | Review inventory aging and slow movers
Quarterly | Estimated tax figures for the CPA
Quarterly | Financial & Cost and Sales & Pricing reports
Annually | Full physical inventory count (Dec 31)
Annually | 1099 list and W-9 check
Annually | Fixed asset and depreciation review
Annually | Year-end packet for the CPA